## Slide 1
12th March
29th March
30th April
14th April
27th May
1. EDA
Investigate feasibility of proposed area of study, identify datasets, resourcing
2. Project Definition
Outline proposed research project. Proposal review and approval by Stakeholder group. Develop project plan and resourcing requests. Gain stakeholder sign-off.
3. Implementation
Execute the proposed research project.
4. Workshop
Stakeholder workshop to review findings and recommendations. Gather feedback and comments for inclusion
5. Project Report
Project report Include feedback and comments
4th June
6. Review
Project Review